## Bug Report
Bug ID | Module | Bug Title | Description | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Status | Date | Status | Retest Date | Remarks
BUG_001 | Candidate Search | Preferred Location Search Not Working | Location search only checks Current Location and ignores Preferred Location. | User logged in; candidate records available. | 1. Open Candidate Search 2. Search using a location present only in Preferred Location 3. Observe results | Candidates matching Current Location OR Preferred Location should be displayed. | Only Current Location matches are returned. | Open | 2026-07-03 | Closed | 2026-07-06 | Retested on Latest build.Working as expected.
BUG_002 | Applicant Search | Selected location chip is missing in UI | The selected location chip (e.g., 'Dubai' displayed inside a blue tag with a close (X) icon) is missing from the Applicant Search page, although it is present in the approved design. | Open the Applicant Search page. | 1. Navigate to Applicant Search. 2. Select a location (e.g., Dubai). 3. Observe the selected filter area. | The selected location should be displayed as a blue chip/tag with the location name and an 'X' icon to remove the filter, matching the approved design. | The selected location chip is not displayed. Users cannot visually identify or remove the selected location filter from the UI. | Open | 2026-07-03 | Open | 2026-07-06 | only single search can be made, multiple search chip is required
BUG_003 | Candidate Search | Keyword search is available only for Location; Skills keyword search is missing | The Candidate Search page provides keyword search/chips only for Location. There is no keyword search field for Skills, making it impossible to filter candidates by skills using keyword chips. | User is logged in and Candidate Search page is open. | 1.Open Candidate Search. 2. Check the available search filters. 3. Try to search candidates by Skills 4. Observe the available keyword search options. | Keyword search/chip functionality should be available for both Location and Skills as per the expected search functionality. | Keyword search/chips are available only for Location. No keyword search field is provided for Skills. | Open | 2026-07-06